## risks
14. Risk Register
ID | Risk Description | Type | Likelihood | Impact
RSK01 | JWT token not validated correctly | Security | Medium | High
RSK02 | ECS Fargate scale-up delay during traffic spike | Availability | Medium | High
RSK03 | Database downtime (PostgreSQL RDS) | Reliability | Low | High
RSK04 | Secrets leakage or misconfigured access | Security | Low | High
RSK05 | API Gateway rate limiting too tight or too loose | Performance | Medium | Medium
RSK06 | Poor local developer experience in isolated Workspaces | Usability | Medium | Medium
RSK07 | Ratings aggregation queries underperform at scale | Performance | Medium | Medium
RSK08 | Cognito service disruption or latency | Availability | Low | Medium
RSK09 | Developer inconsistency in feature branching & testing | Process | Medium | Medium
RSK10 | Feature creep outside MVP scope | Business | High | Medium